## Actions
Action # | Committee | Action | Parties Responsible | Progress | Count
1 | Building Public Safety | Create Mayor's Office of Neighborhood Safety and Engagement. | Mayor's Office of Neighborhood Safety & Engagement | Complete | 1
2 | Building Public Safety | Hold PoliceStat meetings every-other-week to build stronger accountability within BPD and improve service delivery. | Baltimore Police Department, Mayor's Office of Performance & Innovation | Complete | 1
3 | Building Public Safety | Set clear, coordinated public safety vision that addresses violence today and root causes. | Mayor's Office, Mayor's Office of Neighborhood Safety & Engagement, Baltimore City Health Department, Baltimore Police Department | In Progress | 1
4 | Building Public Safety | Commit to monthly updates on major consent decree milestones reached and increase community engagement. | Mayor's Office, Baltimore Police Department | Complete | 1
5 | Building Public Safety | Task Mayor's Office of Neighborhood Safety and Engagement with coordinating public safety strategy. | Mayor's Office of Neighborhood Safety & Engagement | Complete | 1
6 | Building Public Safety | Develop and rollout a strategy to slow the flow of illegal guns into Baltimore City. | Mayor's Office, Baltimore Police Department | In Progress | 1
7 | Building Public Safety | Adopt and support Complete Streets manual increase quality of life and mobility in Baltimore. | Baltimore City Department of Transportation | In Progress | 1
8 | Building Public Safety | Begin implementing a Group Violence Reduction Strategy. | Baltimore Police Department, Mayor's Office of Neighborhood Safety & Engagement | In Progress | 1
9 | Building Public Safety | Meet with community leaders and residents around a shared vision for public safety. | Mayor's Office, Mayor's Office of Neighborhood Safety & Engagement | Not Yet Started | 1
10 | Building Public Safety | Develop a 911 call diversion working group and draft protocol. | Mayor's Office, Mayor's Office of Neighborhood Safety & Engagement | In Progress | 1
11 | Building Public Safety | Restart the Criminal Justice Coordinating Council underneath the Mayor's Office of Neighborhood Safety and Engagement. | Mayor's Office of Neighborhood Safety & Engagement | Not Yet Started | 1
12 | Building Public Safety | Convene the first meeting of the Public Safety Advisory Commission. | Mayor's Office of Neighborhood Safety & Engagement | Not Yet Started | 1
13 | Making Baltimore Equitable | Hire Baltimore's first Chief Equity Officer. | Mayor's Office, Baltimore City Office of Equity & Civil Rights | Complete | 1
14 | Making Baltimore Equitable | Hire a Digital Equity Director. | Mayor's Office | In Progress | 1
15 | Making Baltimore Equitable | Make Baltimore City’s hiring practices more equitable. | Baltimore City Department of Human Resources | Not Yet Started | 1
16 | Making Baltimore Equitable | Identify a senior official in each agency to be responsible for equity. | Mayor's Office | In Progress | 1
17 | Making Baltimore Equitable | Commit to moving Baltimore towards zero waste and begin making shifts toward a more sustainable city. | Mayor's Office, Baltimore City Department of Planning and Baltimore City Department of Public Works | In Progress | 1
18 | Making Baltimore Equitable | Elevate Sustainability Director to a cabinet-level position. | Mayor's Office, Baltimore City Department of Planning | Not Yet Started | 1
19 | Making Baltimore Equitable | Create improved transparency into the retention, attraction, and growth of City neighborhoods. | Baltimore City Department of Housing & Community Development, Baltimore City Department of Planning, Baltimore City Department of Finance | Not Yet Started | 1
20 | Making Baltimore Equitable | Initiate a full reform of the procurement process. | Baltimore City Department of Finance, Baltimore City Bureau of Procurement | In Progress | 1
21 | Making Baltimore Equitable | Activate small and local business preference in the procurement process. | Baltimore City Department of Finance, Baltimore City Bureau of Procurement | Not Yet Started | 1
22 | Making Baltimore Equitable | Prioritize tracking data for City developments and projects that receive TIFs around local hiring and workforce development. | Baltimore Development Corporation | Not Yet Started | 1
23 | Making Baltimore Equitable | Establish a Hiring Task Force to review HR practices to meet equity requirements and continue to professionalize our workforce. | Baltimore City Department of Human Resources | Not Yet Started | 1
24 | Making Baltimore Equitable | Prioritize the Baltimore Greenway Trails Network. | Baltimore City Department of Planning, Baltimore City Department of Transportation, Baltimore City Department of Recreation & Parks | In Progress | 1
25 | Making Baltimore Equitable | Join Climate Mayors in supporting the spirit and goals of the Paris Climate Agreement. | Baltimore City Department of Planning | Complete | 1
26 | Prioritizing Our Youth | Support the overrides of the Blueprint for Maryland's Future and Built to Learn. | Mayor's Office, Maryland General Assembly | In Progress | 1
27 | Prioritizing Our Youth | Prepare to significantly increase the capacity of virtual YouthWorks in 2021. | Mayor's Office of Employment Development | In Progress | 1
28 | Prioritizing Our Youth | Begin implementation of the Elijah Cummings Healing City Act to ensure trauma-informed practice across city government. | Mayor's Office of Children and Family Success, Baltimore City Health Department | Complete | 1
29 | Prioritizing Our Youth | Develop plan for equitable and age-appropriate access in partnership with sports, arts, and cultural institutions that create recreational services during this unprecedented pandemic. | Baltimore City Department of Recreation & Parks | Not Yet Started | 1
30 | Prioritizing Our Youth | Partner with the Youth Commission to establish cabinet member youth shadows. | Baltimore City Youth Commission, Mayor's Office of Children and Family Success | Not Yet Started | 1
31 | Prioritizing Our Youth | Join Mayors for Guaranteed Income with a focus on supporting youth and families. | Mayor's Office of Children and Family Success | Complete | 1
32 | Prioritizing Our Youth | Host biannual Youth Summits with the Mayor to bring attention to youth-focused issues in the City. | Mayor's Office of Children and Family Success | Not Yet Started | 1
33 | Building Public Trust | Hire Baltimore's first City Administrator. | Mayor's Office | Complete | 1
34 | Building Public Trust | Kick off community engagement plan to introduce City Administrator and other senior officials to public. | Mayor's Office | In Progress | 1
35 | Building Public Trust | Establish, through CitiStat, performance management to ensure greater accountability and more equitable delivery of City services for residents. | Mayor's Office of Performance & Innovation | In Progress | 1
36 | Building Public Trust | Restore recycling services, which were suspended due to COVID-19. | Baltimore City Department of Public Works | Complete | 1
37 | Building Public Trust | Announce an action plan to reform Baltimore's water billing system. | Baltimore City Department of Public Works | In Progress | 1
38 | Building Public Trust | Appoint a permanent Department of Public Works Director. | Baltimore City Department of Public Works | In Progress | 1
39 | Building Public Trust | Appoint a permanent Housing Commissioner. | Baltimore City Department of Housing & Community Development | In Progress | 1
40 | Building Public Trust | Appoint a permanent Homeless Services Director. | Mayor's Office of Homeless Services | In Progress | 1
41 | Building Public Trust | Initiate a process to remove the backlog of transportation and infrastructure related 311 service requests in historically marginalized communities. | Baltimore City Department of Public Works, Baltimore City Department of Transportation | Not Yet Started | 1
42 | Building Public Trust | Initiate a process improvement project to establish a more seamless system for applying for and receiving city-owned properties. | Baltimore City Department of Housing & Community Development | Not Yet Started | 1
43 | Building Public Trust | Make stronger commitments to cleaning up sewage backups. | Baltimore City Department of Public Works | Not Yet Started | 1
44 | Building Public Trust | Expand who has to file annual financial disclosures. | Baltimore City Ethics Board | Not Yet Started | 1
45 | COVID-19 Recovery | Develop and communicate a COVID-19 vaccination prioritization strategy. | Baltimore City Health Department | Complete | 1
46 | COVID-19 Recovery | Create a dashboard to track CARES act funding to ensure equitable distribution. | Baltimore City Department of Finance | Not Yet Started | 1
47 | COVID-19 Recovery | Use Rapid Rehousing dollars to move additional people and families experiencing homelessness to more permanent housing. | Mayor's Office of Homeless Services | In Progress | 1
48 | COVID-19 Recovery | Extend emergency shelter in local hotels when CARES Act funding expires. | Mayor's Office of Homeless Services | Complete | 1
49 | COVID-19 Recovery | Cap restaurant delivery fees on third-party app services. | Baltimore City Department of Finance | Complete | 1
50 | COVID-19 Recovery | Identify clear point of contact for local businesses to more effectively navigate city government. | Mayor's Office, Baltimore Development Corporation | Not Yet Started | 1
51 | COVID-19 Recovery | Deploy $6 million in direct support for families impacted by COVID-19. | Mayor's Office of Children and Family Success | In Progress | 1
52 | COVID-19 Recovery | Expand Baltimore's eviction prevention efforts. | Baltimore City Department of Housing and Community Development, Mayor's Office of Children and Family Success | Not Yet Started | 1
53 | COVID-19 Recovery | Implement the COVID-19: Prevention, Control, and Support strategy to mitigate the disproportionate impact the pandemic on the Latino community. | Baltimore City Health Department, Mayor's Office of Immigrant Affairs | Complete | 1
54 | Responsible Stewardship of City Resources | Begin holistic, top-to-bottom assessment of city agencies and process to inventory city property. | Baltimore City Department of Planning | In Progress | 1
55 | Responsible Stewardship of City Resources | Begin a holistic review of tax credits to address inefficiencies, redundancies, or new credits that would build a more equitable city. | Baltimore City Department of Finance | Not Yet Started | 1
56 | Responsible Stewardship of City Resources | Expand community engagement in the budget process. | Baltimore City Department of Finance | In Progress | 1
57 | Responsible Stewardship of City Resources | Commit to updating the City's 10-year financial plan. | Baltimore City Department of Finance | In Progress | 1
58 | Responsible Stewardship of City Resources | Design and release Open Checkbook for Baltimore to increase transparency and accountability. | Mayor's Office of Performance and Innovation, Baltimore City Department of Finance | Not Yet Started | 1

## Actions As Provided 129 (hidden)
Building Public Safety |  | Status | Exec Team
Create Mayor's Office of Neighborhood Safety and Engagement. | MONSE | Complete | Sunny
Establish monthly PoliceStat meetings to build stronger accountability within BPD and improve service delivery. | BPD | Complete/Will have updates | Sunny
Set clear, coordinated public safety vision that addresses violence today and root causes. | MO, MONSE, BCHD, BPD |  | Sunny
Task Mayor's Office of Neighborhood Safety and Engagement with coordinating public safety strategy. | MONSE | In Progress | Sunny
Introduce local housing voucher program. | DHCD |  | Daniel
Adopt and support Complete Streets manual increase quality of life and mobility in Baltimore. | DOT |  | Daniel
Begin implementing a Group Violence Reduction Strategy. | BPD, MONSE | In Progress | Sunny
Proactively deploy City agencies to address environmental concerns that contribute to neighborhood safety. | BPD, MONSE, DPW, DHCD, BCHD |  | Sunny/Chris/Daniel
Meet with community leaders and residents around a shared vision for public safety. | MO, MONSE |  | Sunny/Scott/Stefanie
Convene the first meeting of the Public Safety Advisory Commission. | MO |  | Michael/Sunny
Making Baltimore Equitable
Hire Baltimore's first Chief Equity Officer. | MO, ECR | Complete | Chris/Michael
Hire a Digital Equity Director. | MO |  | Michael
Identify a senior official in each agency to be responsible for equity and sustainable action. | MO |  | Chris
Commit to Baltimore's zero waste goals and begin shifts toward a more sustainable city. | MO, DOP |  | Chris
Elevate Sustainability Director to a cabinet-level position. | MO, DOP |  | Chris/Michael
Remove the most vulnerable residents from tax sale. | DOF |  | Daniel
Announce a back-to-basics community development strategy that centers community input. | MO, DHCD |  | Daniel
Create a Neighborhood Stat to track progress on retention, attraction, and growth in neighborhoods. | DHCD, OPI |  | Daniel
Begin top-to-bottom review of the procurement process. | DOF, BOP |  | Michael/Chris
Activate small and local business preference in the procurement process. | DOF, BOP |  | Chris/Daniel
Prioritize tracking data for City developments and projects that receive TIFs around local hiring and workforce development. | BDC |  | Daniel
Establish a Hiring Task Force to review HR practices, policy interventions, best practices, and barriers through a lens of equity and meet workforce needs. | DHR |  | Chris/Michael/Leslie
Establish a resident preference program for City jobs. | DHR |  | Chris
Prioritize the Baltimore Greenway Trails Network. | DOP, DOT, DRP |  | Daniel
Join Climate Mayors in supporting the spirit and goals of the Paris Climate Agreement. | DOP | Complete | Stefanie
Prioritizing Our Youth
Support the overrides of the Blueprint for Maryland's Future and Built to Learn. | MO, MGA | In Progress | Natasha
Prepare to significantly increase the capacity of virtual YouthWorks in 2021. | MOED | In Progress | Michael
Begin implementation of the Elijah Cummings Healing City Act to ensure trauma-informed practice across city government. | BCHD, MONSE | In Progress | Natasha/Sunny
Develop plan for equitable and age-appropriate access in partnership with sports, arts, and cultural institutions that create recreational services during this unprecedented pandemic. | DRP |  | Scott
Building Public Trust
Hire Baltimore's first Chief Administrative Officer. | MO | Complete | Michael
Kick off community engagement plan to introduce Chief Administrative Officer and other senior officials to public. | MO |  | Stefanie/Scott
Establish a regular Stat program to ensure greater accountability and more equitable service delivery across City government. | OPI | In Progress | Daniel
Restore recycling services, which were suspended due to COVID-19. | DPW | Complete | Daniel
Announce plan to reform the water billing program. | DPW | In Progress | Daniel
Appoint a permanent Housing Commissioner. | DHCD |  | Chris/Michael
Appoint a permanent Homeless Services director. | MOHS |  | Chris/Michael
Initiate a Fix-it First campaign to fill backlog of transportation and infrastructure related 311 service requests, particularly where there has historically been a longer response time. | DPW, DOT |  | Chris/Daniel
Publish a clear and concise set of procedures to apply for and receive city-owned properties for development. | DHCD |  | Daniel
Make stronger commitments to cleaning up sewage backups. | DPW |  | Daniel
COVID-19 Recovery
Develop and communicate a COVID-19 vaccination prioritization strategy. | BCHD | Complete | Sunny
Create a dashboard to track CARES act funding to ensure equitable distribution. | DOF |  | Daniel
Use Rapid Rehousing CARES Act dollars to move 500 people and families to more permanent housing. | MOHS | In Progress | Daniel
Extend emergency shelter in local hotels when CARES Act funding expires. | MOHS | Complete | Daniel
Cap restaurant delivery fees on third-party app services. | DOF | Complete | Natasha
Identify clear point of contact for local businesses to more effectively navigate city government. | MO, BDC |  | Daniel
Responsible Stewardship of City Resources
Begin holistic, top-to-bottom assessment of city agencies and process to inventory city property. | DGS |  | Chris/Daniel
Begin a holistic review of tax credits to address inefficiencies, redundancies, or new credits that would build a more equitable city. | DOF |  | Daniel
Announce new criteria for evaluation of capital budget requests. | MO, DOF |  | Chris/Michael
Expand community engagement in the budget process. | DOF |  | Daniel
Commit to updating the City's 10-year financial plan. | DOF |  | Chris/Daniel
Design and release Open Checkbook for Baltimore to increase transparency and accountability. | BCIT, DOF |  | Daniel

## Days
Mayoral First 100 Days Number | Date | Weekday | Milestone | Notes
1 | 2020-12-08 | 2020-12-08 | Mayor Scott Inauguration
2 | 2020-12-09 | 2020-12-09
3 | 2020-12-10 | 2020-12-10
4 | 2020-12-11 | 2020-12-11
5 | 2020-12-12 | 2020-12-12
6 | 2020-12-13 | 2020-12-13
7 | 2020-12-14 | 2020-12-14
8 | 2020-12-15 | 2020-12-15
9 | 2020-12-16 | 2020-12-16
10 | 2020-12-17 | 2020-12-17
11 | 2020-12-18 | 2020-12-18
12 | 2020-12-19 | 2020-12-19
13 | 2020-12-20 | 2020-12-20
14 | 2020-12-21 | 2020-12-21
15 | 2020-12-22 | 2020-12-22
16 | 2020-12-23 | 2020-12-23
17 | 2020-12-24 | 2020-12-24
18 | 2020-12-25 | 2020-12-25
19 | 2020-12-26 | 2020-12-26
20 | 2020-12-27 | 2020-12-27
21 | 2020-12-28 | 2020-12-28
22 | 2020-12-29 | 2020-12-29
23 | 2020-12-30 | 2020-12-30
24 | 2020-12-31 | 2020-12-31
25 | 2021-01-01 | 2021-01-01 | First quarter ends
26 | 2021-01-02 | 2021-01-02
27 | 2021-01-03 | 2021-01-03
28 | 2021-01-04 | 2021-01-04
29 | 2021-01-05 | 2021-01-05
30 | 2021-01-06 | 2021-01-06
31 | 2021-01-07 | 2021-01-07
32 | 2021-01-08 | 2021-01-08
33 | 2021-01-09 | 2021-01-09
34 | 2021-01-10 | 2021-01-10
35 | 2021-01-11 | 2021-01-11
36 | 2021-01-12 | 2021-01-12
37 | 2021-01-13 | 2021-01-13
38 | 2021-01-14 | 2021-01-14
39 | 2021-01-15 | 2021-01-15
40 | 2021-01-16 | 2021-01-16
41 | 2021-01-17 | 2021-01-17
42 | 2021-01-18 | 2021-01-18
43 | 2021-01-19 | 2021-01-19
44 | 2021-01-20 | 2021-01-20
45 | 2021-01-21 | 2021-01-21
46 | 2021-01-22 | 2021-01-22
47 | 2021-01-23 | 2021-01-23
48 | 2021-01-24 | 2021-01-24
49 | 2021-01-25 | 2021-01-25
50 | 2021-01-26 | 2021-01-26 | First half ends
51 | 2021-01-27 | 2021-01-27
52 | 2021-01-28 | 2021-01-28
53 | 2021-01-29 | 2021-01-29
54 | 2021-01-30 | 2021-01-30
55 | 2021-01-31 | 2021-01-31
56 | 2021-02-01 | 2021-02-01
57 | 2021-02-02 | 2021-02-02
58 | 2021-02-03 | 2021-02-03
59 | 2021-02-04 | 2021-02-04
60 | 2021-02-05 | 2021-02-05
61 | 2021-02-06 | 2021-02-06
62 | 2021-02-07 | 2021-02-07
63 | 2021-02-08 | 2021-02-08
64 | 2021-02-09 | 2021-02-09
65 | 2021-02-10 | 2021-02-10
66 | 2021-02-11 | 2021-02-11
67 | 2021-02-12 | 2021-02-12
68 | 2021-02-13 | 2021-02-13
69 | 2021-02-14 | 2021-02-14
70 | 2021-02-15 | 2021-02-15
71 | 2021-02-16 | 2021-02-16
72 | 2021-02-17 | 2021-02-17
73 | 2021-02-18 | 2021-02-18
74 | 2021-02-19 | 2021-02-19
75 | 2021-02-20 | 2021-02-20 | Third quarter ends
76 | 2021-02-21 | 2021-02-21
77 | 2021-02-22 | 2021-02-22
78 | 2021-02-23 | 2021-02-23
79 | 2021-02-24 | 2021-02-24
80 | 2021-02-25 | 2021-02-25
81 | 2021-02-26 | 2021-02-26
82 | 2021-02-27 | 2021-02-27
83 | 2021-02-28 | 2021-02-28
84 | 2021-03-01 | 2021-03-01
85 | 2021-03-02 | 2021-03-02
86 | 2021-03-03 | 2021-03-03
87 | 2021-03-04 | 2021-03-04
88 | 2021-03-05 | 2021-03-05
89 | 2021-03-06 | 2021-03-06
90 | 2021-03-07 | 2021-03-07
91 | 2021-03-08 | 2021-03-08
92 | 2021-03-09 | 2021-03-09
93 | 2021-03-10 | 2021-03-10
94 | 2021-03-11 | 2021-03-11
95 | 2021-03-12 | 2021-03-12
96 | 2021-03-13 | 2021-03-13
97 | 2021-03-14 | 2021-03-14
98 | 2021-03-15 | 2021-03-15
99 | 2021-03-16 | 2021-03-16
100 | 2021-03-17 | 2021-03-17 | End of first 100 days
Formulas:
Weekday = [Date]

## Committees
Number | Name | Priority
1 | Building Public Safety | Reimagining Public Safety and Public Accountability
2 | Making Baltimore Equitable | Commit to Equity at the Core of City Services
3 | Prioritizing Our Youth | Expanding Opportunities for All of Baltimore's Youth
4 | Building Public Trust | Establishing Government Accountability from the Top Down
5 | COVID-19 Recovery | Leading an Effective Coronavirus Response for All
6 | Responsible Stewardship of City Resources | Aligning Resources to Ensure Fiscal Stability and Innovation

## Progress Updates
Number | Date | Update HTML
1 | 2021-02-24 | <p><span style="font-size: 16px;">Every week, our team will share updates from across our government to keep you involved in our work making Baltimore a safer, healthier, and more equitable city. Be sure to check back in to stay updated on our achievements during these hundred days and beyond!&nbsp;</span></p> <p><span style="font-size: 16px;">Since Mayor Scott took office on December 8th, 2020, we&rsquo;ve been hard at work improving Baltimore government. Below are a few highlights of Mayor Scott&rsquo;s achievements:</span></p> <ul> <li style="margin-left: 20px;"><span style="font-size: 16px;">Created and staffed the Mayor&rsquo;s Office of Neighborhood Safety and Engagement</span></li> <li style="margin-left: 20px;"><span style="font-size: 16px;">Launched the first PoliceStat meeting to coordinate services and increase accountability</span></li> <li style="margin-left: 20px;"><span style="font-size: 16px;">Hired Baltimore&rsquo;s first Chief Equity Officer</span></li> <li style="margin-left: 20px;"><span style="font-size: 16px;">Hired Baltimore&rsquo;s first Chief Administrative Officer</span></li> </ul> <p><span style="font-size: 16px;">We have bold plans to reshape Baltimore&rsquo;s government over the coming months. This work will involve unprecedented transparency, accountability, and urgency as we seek to build a Baltimore where every resident can thrive.</span></p>
2

## Parties
Organization | Organization Full Name | Organization Website
BCHD | Baltimore City Health Department | health.baltimorecity.gov
BCIT | Baltimore City Information & Technology | technology.baltimorecity.gov
BDC | Baltimore Development Corporation | baltimoredevelopment.com
BOP | Baltimore City Bureau of Procurement | procurement.baltimorecity.gov
BPD | Baltimore Police Department | baltimorepolice.org
DGS | Baltimore City Department of General Services | generalservices.baltimorecity.gov
DHCD | Baltimore City Department of Housing & Community Development | dhcd.baltimorecity.gov
DHR | Baltimore City Department of Human Resources | https://humanresources.baltimorecity.gov/
DOF | Baltimore City Department of Finance | finance.baltimorecity.gov
DOP | Baltimore City Department of Planning | planning.baltimorecity.gov
DOT | Baltimore City Department of Transportation | transportation.baltimorecity.gov
DPW | Baltimore City Department of Public Works | publicworks.baltimorecity.gov
DRP | Baltimore City Department of Recreation & Parks | bcrp.baltimorecity.gov
ECR | Baltimore City Office of Equity & Civil Rights | civilrights.baltimorecity.gov
MGA | Maryland General Assembly | mgaleg.maryland.gov
MO | Mayor's Office | mayor.baltimorecity.gov
MOED | Mayor's Office of Employment Development | moed.baltimorecity.gov
MOHS | Mayor's Office of Homeless Services | homeless.baltimorecity.gov
MONSE | Mayor's Office of Neighborhood Safety & Engagement | mocj.baltimorecity.gov
OPI | Mayor's Office of Performance & Innovation | https://opi.baltimorecity.gov/