## Actions
Action # | Committee | Action | Parties Responsible | Progress | Count
1 | Creating Agency Infrastructure | Hire staff to lead the implementation of gun violence strategy oversight, inter-agency coordination, community engagement and empowerment, policy development and support, and community capacity building. |  | In Progress | 1
2 | Public Health Approach to Violence | Evaluate Safe Streets to identify steps for building capacity and develop a coordinated street outreach and violence interruption strategy. |  | In Progress | 1
3 | Public Health Approach to Violence | Engage Cities United Peace Challenge technical assistance on coordinated shooting response systems. |  | In Progress | 1
4 | Community Engagement and Inter-Agency Collaboration | Support the Mayor in issuing and monitoring implementation of a citywide directive laying out inter-agency roles and expectations in supporting GVRS. |  | Not Started | 1
5 | Public Health Approach to Violence | Award the adult support and outreach provider contract for GVRS. |  | Complete | 1
6 | Public Health Approach to Violence | Establish initial inter-agency coordination and governance structures for GVRS. |  | Not Yet Started | 1
7 | Evaluation and Accountability | Develop strategic key performance indicators for GVRSStat. |  | In Progress | 1
8 | Community Engagement and Inter-Agency Collaboration | Develop a communications plan for GVRS. |  | In Progress | 1
9 | Community Engagement and Inter-Agency Collaboration | Meet with BPD, community leaders, and residents around a shared vision for public safety and community policing. |  | In Progress | 1
10 | Public Health Approach to Violence | Initiate a landscape analysis of CBOs with services that would be integral to a comprehensive public health approach to violence prevention. |  | Not Yet Started | 1
11 | Community Engagement and Inter-Agency Collaboration | Convene Public Safety Advisory Commission. |  | In Progress | 1
Note on A1: Im comfortable with changing this, but let me know if you want me to hold for approval. -Markele Cullins ---- Please do not edit this column. This will update programmatically based on data in the Progress Updates tab. -Brendan Hellweg

## Parties
Organization | Organization Full Name | Organization Website

## Actions As Provided 129 (hidden)
Building Public Safety |  | Status | Exec Team
Create Mayor's Office of Neighborhood Safety and Engagement. | MONSE | Complete | Sunny
Establish monthly PoliceStat meetings to build stronger accountability within BPD and improve service delivery. | BPD | Complete/Will have updates | Sunny
Set clear, coordinated public safety vision that addresses violence today and root causes. | MO, MONSE, BCHD, BPD |  | Sunny
Task Mayor's Office of Neighborhood Safety and Engagement with coordinating public safety strategy. | MONSE | In Progress | Sunny
Introduce local housing voucher program. | DHCD |  | Daniel
Adopt and support Complete Streets manual increase quality of life and mobility in Baltimore. | DOT |  | Daniel
Begin implementing a Group Violence Reduction Strategy. | BPD, MONSE | In Progress | Sunny
Proactively deploy City agencies to address environmental concerns that contribute to neighborhood safety. | BPD, MONSE, DPW, DHCD, BCHD |  | Sunny/Chris/Daniel
Meet with community leaders and residents around a shared vision for public safety. | MO, MONSE |  | Sunny/Scott/Stefanie
Convene the first meeting of the Public Safety Advisory Commission. | MO |  | Michael/Sunny
Making Baltimore Equitable
Hire Baltimore's first Chief Equity Officer. | MO, ECR | Complete | Chris/Michael
Hire a Digital Equity Director. | MO |  | Michael
Identify a senior official in each agency to be responsible for equity and sustainable action. | MO |  | Chris
Commit to Baltimore's zero waste goals and begin shifts toward a more sustainable city. | MO, DOP |  | Chris
Elevate Sustainability Director to a cabinet-level position. | MO, DOP |  | Chris/Michael
Remove the most vulnerable residents from tax sale. | DOF |  | Daniel
Announce a back-to-basics community development strategy that centers community input. | MO, DHCD |  | Daniel
Create a Neighborhood Stat to track progress on retention, attraction, and growth in neighborhoods. | DHCD, OPI |  | Daniel
Begin top-to-bottom review of the procurement process. | DOF, BOP |  | Michael/Chris
Activate small and local business preference in the procurement process. | DOF, BOP |  | Chris/Daniel
Prioritize tracking data for City developments and projects that receive TIFs around local hiring and workforce development. | BDC |  | Daniel
Establish a Hiring Task Force to review HR practices, policy interventions, best practices, and barriers through a lens of equity and meet workforce needs. | DHR |  | Chris/Michael/Leslie
Establish a resident preference program for City jobs. | DHR |  | Chris
Prioritize the Baltimore Greenway Trails Network. | DOP, DOT, DRP |  | Daniel
Join Climate Mayors in supporting the spirit and goals of the Paris Climate Agreement. | DOP | Complete | Stefanie
Prioritizing Our Youth
Support the overrides of the Blueprint for Maryland's Future and Built to Learn. | MO, MGA | In Progress | Natasha
Prepare to significantly increase the capacity of virtual YouthWorks in 2021. | MOED | In Progress | Michael
Begin implementation of the Elijah Cummings Healing City Act to ensure trauma-informed practice across city government. | BCHD, MONSE | In Progress | Natasha/Sunny
Develop plan for equitable and age-appropriate access in partnership with sports, arts, and cultural institutions that create recreational services during this unprecedented pandemic. | DRP |  | Scott
Building Public Trust
Hire Baltimore's first Chief Administrative Officer. | MO | Complete | Michael
Kick off community engagement plan to introduce Chief Administrative Officer and other senior officials to public. | MO |  | Stefanie/Scott
Establish a regular Stat program to ensure greater accountability and more equitable service delivery across City government. | OPI | In Progress | Daniel
Restore recycling services, which were suspended due to COVID-19. | DPW | Complete | Daniel
Announce plan to reform the water billing program. | DPW | In Progress | Daniel
Appoint a permanent Housing Commissioner. | DHCD |  | Chris/Michael
Appoint a permanent Homeless Services director. | MOHS |  | Chris/Michael
Initiate a Fix-it First campaign to fill backlog of transportation and infrastructure related 311 service requests, particularly where there has historically been a longer response time. | DPW, DOT |  | Chris/Daniel
Publish a clear and concise set of procedures to apply for and receive city-owned properties for development. | DHCD |  | Daniel
Make stronger commitments to cleaning up sewage backups. | DPW |  | Daniel
COVID-19 Recovery
Develop and communicate a COVID-19 vaccination prioritization strategy. | BCHD | Complete | Sunny
Create a dashboard to track CARES act funding to ensure equitable distribution. | DOF |  | Daniel
Use Rapid Rehousing CARES Act dollars to move 500 people and families to more permanent housing. | MOHS | In Progress | Daniel
Extend emergency shelter in local hotels when CARES Act funding expires. | MOHS | Complete | Daniel
Cap restaurant delivery fees on third-party app services. | DOF | Complete | Natasha
Identify clear point of contact for local businesses to more effectively navigate city government. | MO, BDC |  | Daniel
Responsible Stewardship of City Resources
Begin holistic, top-to-bottom assessment of city agencies and process to inventory city property. | DGS |  | Chris/Daniel
Begin a holistic review of tax credits to address inefficiencies, redundancies, or new credits that would build a more equitable city. | DOF |  | Daniel
Announce new criteria for evaluation of capital budget requests. | MO, DOF |  | Chris/Michael
Expand community engagement in the budget process. | DOF |  | Daniel
Commit to updating the City's 10-year financial plan. | DOF |  | Chris/Daniel
Design and release Open Checkbook for Baltimore to increase transparency and accountability. | BCIT, DOF |  | Daniel

## Days
MONSE First 100 Days | Date | Weekday | Milestone | Notes
1 | 2021-02-23 | 2021-02-23 | Mayor Approves Plan Draft
2 | 2021-02-24 | 2021-02-24
3 | 2021-02-25 | 2021-02-25
4 | 2021-02-26 | 2021-02-26
5 | 2021-02-27 | 2021-02-27
6 | 2021-02-28 | 2021-02-28
7 | 2021-03-01 | 2021-03-01
8 | 2021-03-02 | 2021-03-02
9 | 2021-03-03 | 2021-03-03
10 | 2021-03-04 | 2021-03-04
11 | 2021-03-05 | 2021-03-05
12 | 2021-03-06 | 2021-03-06
13 | 2021-03-07 | 2021-03-07
14 | 2021-03-08 | 2021-03-08
15 | 2021-03-09 | 2021-03-09
16 | 2021-03-10 | 2021-03-10
17 | 2021-03-11 | 2021-03-11
18 | 2021-03-12 | 2021-03-12
19 | 2021-03-13 | 2021-03-13
20 | 2021-03-14 | 2021-03-14
21 | 2021-03-15 | 2021-03-15
22 | 2021-03-16 | 2021-03-16
23 | 2021-03-17 | 2021-03-17
24 | 2021-03-18 | 2021-03-18
25 | 2021-03-19 | 2021-03-19 | First quarter ends
26 | 2021-03-20 | 2021-03-20
27 | 2021-03-21 | 2021-03-21
28 | 2021-03-22 | 2021-03-22
29 | 2021-03-23 | 2021-03-23
30 | 2021-03-24 | 2021-03-24
31 | 2021-03-25 | 2021-03-25
32 | 2021-03-26 | 2021-03-26
33 | 2021-03-27 | 2021-03-27
34 | 2021-03-28 | 2021-03-28
35 | 2021-03-29 | 2021-03-29
36 | 2021-03-30 | 2021-03-30
37 | 2021-03-31 | 2021-03-31
38 | 2021-04-01 | 2021-04-01
39 | 2021-04-02 | 2021-04-02
40 | 2021-04-03 | 2021-04-03
41 | 2021-04-04 | 2021-04-04
42 | 2021-04-05 | 2021-04-05
43 | 2021-04-06 | 2021-04-06
44 | 2021-04-07 | 2021-04-07
45 | 2021-04-08 | 2021-04-08
46 | 2021-04-09 | 2021-04-09
47 | 2021-04-10 | 2021-04-10
48 | 2021-04-11 | 2021-04-11
49 | 2021-04-12 | 2021-04-12
50 | 2021-04-13 | 2021-04-13 | First half ends
51 | 2021-04-14 | 2021-04-14
52 | 2021-04-15 | 2021-04-15
53 | 2021-04-16 | 2021-04-16
54 | 2021-04-17 | 2021-04-17
55 | 2021-04-18 | 2021-04-18
56 | 2021-04-19 | 2021-04-19
57 | 2021-04-20 | 2021-04-20
58 | 2021-04-21 | 2021-04-21
59 | 2021-04-22 | 2021-04-22
60 | 2021-04-23 | 2021-04-23
61 | 2021-04-24 | 2021-04-24
62 | 2021-04-25 | 2021-04-25
63 | 2021-04-26 | 2021-04-26
64 | 2021-04-27 | 2021-04-27
65 | 2021-04-28 | 2021-04-28
66 | 2021-04-29 | 2021-04-29
67 | 2021-04-30 | 2021-04-30
68 | 2021-05-01 | 2021-05-01
69 | 2021-05-02 | 2021-05-02
70 | 2021-05-03 | 2021-05-03
71 | 2021-05-04 | 2021-05-04
72 | 2021-05-05 | 2021-05-05
73 | 2021-05-06 | 2021-05-06
74 | 2021-05-07 | 2021-05-07
75 | 2021-05-08 | 2021-05-08 | Third quarter ends
76 | 2021-05-09 | 2021-05-09
77 | 2021-05-10 | 2021-05-10
78 | 2021-05-11 | 2021-05-11
79 | 2021-05-12 | 2021-05-12
80 | 2021-05-13 | 2021-05-13
81 | 2021-05-14 | 2021-05-14
82 | 2021-05-15 | 2021-05-15
83 | 2021-05-16 | 2021-05-16
84 | 2021-05-17 | 2021-05-17
85 | 2021-05-18 | 2021-05-18
86 | 2021-05-19 | 2021-05-19
87 | 2021-05-20 | 2021-05-20
88 | 2021-05-21 | 2021-05-21
89 | 2021-05-22 | 2021-05-22
90 | 2021-05-23 | 2021-05-23
91 | 2021-05-24 | 2021-05-24
92 | 2021-05-25 | 2021-05-25
93 | 2021-05-26 | 2021-05-26
94 | 2021-05-27 | 2021-05-27
95 | 2021-05-28 | 2021-05-28
96 | 2021-05-29 | 2021-05-29
97 | 2021-05-30 | 2021-05-30
98 | 2021-05-31 | 2021-05-31
99 | 2021-06-01 | 2021-06-01
100 | 2021-06-02 | 2021-06-02 | End of first 100 days
Formulas:
Weekday = [Date]
Note on A1: Worth thinking about whether they want a true "first X days" system or if something with looser time restrictions is a better fit -Brendan Hellweg

## Committees
Number | Name | Priority
1 | Creating Agency Infrastructure
2 | Public Health Approach to Violence
3 | Community Engagement and Inter-Agency Collaboration
4 | Evaluation and Accountability